## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Teams & Projects
| Table 1 | Teams & Projects
Project Details
| Table 1 | Project Details
Requirements Checklist
| Table 1 | Requirements Checklist
Shared Requirements
| Table 1 | Shared Requirements
Timeline
| Table 1 | Timeline
Grading Sheet
| Table 1 | Grading Sheet

## Teams & Projects
Mobile Internship - Graduation Projects (6 Teams)
Difficulty: Medium ¦ Duration: 4 weeks, 11 Aug 2026 - 31 August 2026 ¦ Platform: choose one (Android/Kotlin, iOS/Swift, or Flutter) ¦ Req 1-6 = core (must ship), Req 7-8 = stretch
Team | Member 1 | Member 2 | Project | Difficulty | Main Skills Practiced
5 | Mohamed Amr Sabry | Tya Magued | SnapNote - Notes with Photos & Voice | Medium | Camera, audio recording, file storage, search

## Project Details
Project Details - each requirement has its own column. Req 1-6 (blue) are CORE and must ship by 6 Sep. Req 7-8 (orange) are STRETCH - only if the core is finished.
Team | Project | Goal | Req 1 (core) | Req 2 (core) | Req 3 (core) | Req 4 (core) | Req 5 (core) | Req 6 (core) | Req 7 (stretch) | Req 8 (stretch) | Technical Challenge (the medium part) | Suggested Tools / API | Definition of Done | Optional Bonus
5 | SnapNote - Notes with Photos & Voice | A rich notes app where a note can contain text, photos and voice memos. | Create a note containing text, photos and voice memos | Capture a photo in-app or pick one from the gallery | Record, play and delete a voice memo with a duration display | Attachments saved into app storage, not just a URI reference | Search across note titles and body text | Tags or folders with filtering | Pin a note to the top; swipe to delete with Undo | Share a note as text plus images | File and media lifecycle: recording audio with correct permissions, saving attachments into app-private storage, cleaning up orphan files when a note is deleted, and keeping large images from blowing up memory. | CameraX / AVFoundation / image_picker - MediaRecorder + MediaPlayer / AVAudioRecorder - Room / Core Data - Coil / Kingfisher | Create a note with 3 photos and a 30-second voice memo, restart the app, play it back. Delete the note - its files are removed from storage. | Speech-to-text to turn a voice memo into note text

## Requirements Checklist
Requirements Checklist - one row per requirement, for weekly tracking
Status values: Not started / In progress / Done. Core = must ship by 6 Sep. Stretch = only after the core is done.
Team | Members | Project | Req # | Priority | Requirement | Status
5 | Mohamed Amr Sabry / Tya Magued | SnapNote - Notes with Photos & Voice | 1 | Core | Create a note containing text, photos and voice memos | Not started
5 | Mohamed Amr Sabry / Tya Magued | SnapNote - Notes with Photos & Voice | 2 | Core | Capture a photo in-app or pick one from the gallery | Not started
5 | Mohamed Amr Sabry / Tya Magued | SnapNote - Notes with Photos & Voice | 3 | Core | Record, play and delete a voice memo with a duration display | Not started
5 | Mohamed Amr Sabry / Tya Magued | SnapNote - Notes with Photos & Voice | 4 | Core | Attachments saved into app storage, not just a URI reference | Not started
5 | Mohamed Amr Sabry / Tya Magued | SnapNote - Notes with Photos & Voice | 5 | Core | Search across note titles and body text | Not started
5 | Mohamed Amr Sabry / Tya Magued | SnapNote - Notes with Photos & Voice | 6 | Core | Tags or folders with filtering | Not started
5 | Mohamed Amr Sabry / Tya Magued | SnapNote - Notes with Photos & Voice | 7 | Stretch | Pin a note to the top; swipe to delete with Undo | Not started
5 | Mohamed Amr Sabry / Tya Magued | SnapNote - Notes with Photos & Voice | 8 | Stretch | Share a note as text plus images | Not started

## Shared Requirements
Requirements That Apply To All 6 Teams
# | Requirement | What we check
1 | Architecture | MVVM or MVI with three clear layers (UI / domain / data) and dependency injection. No API or database call written directly inside a screen file.
2 | State management | One source of truth per screen. Configuration changes and process death do not lose the user's state.
3 | Git | GitHub repo, feature branches, pull requests reviewed by the teammate, meaningful commit messages. Both members commit every week.
4 | UI states | Every screen that loads data handles loading, empty, error and success. Errors offer a retry.
5 | Permissions | Any runtime permission has a rationale screen and a working 'permanently denied' path that sends the user to Settings.
6 | Stability | No crash during the demo. Handles no internet, an empty API response and invalid input.
7 | Testing | At least 3 unit tests on business logic (ViewModel or repository) and 1 UI test, all passing.
8 | README | What the app does, how to run it, API key setup, an architecture diagram, 4-5 screenshots, and known limitations.
9 | Build | A signed APK or a TestFlight / installable build the mentor can run.
10 | Demo | 15-minute live demo + 10 minutes of code questions. Both members present and must explain any part of the code, not only their own.
Out of scope for every project:
No real payments, no real user data, and no custom backend built from scratch. Use free public APIs, the Firebase free tier, sandbox services, or local mock data.

## Timeline
4-Week Timeline - 11 August to 31 August 2026 (same for all teams)
This is a short runway. Req 1-6 are the graded core; Req 7-8 are stretch. A team that ships 6 solid requirements scores higher than one that half-builds 8.
Week | Dates | Focus | Deliverable at the end of the week | Mentor Checkpoint
Week 1 | 11 - 16 Aug | Setup, architecture & first screens | Platform chosen, repo created, wireframes done, API keys working, requirements split between the two members, navigation between all screens, data models and repository interfaces in place. | Kickoff (Tue 11 Aug) + Checkpoint 1 (Sun 16 Aug)
Week 2 | 17 - 23 Aug | Core requirements 1-3 | The main list / main flow works end to end with real data from the API or the local database. Detail screen started. | Checkpoint 2 - mid demo + Git contribution check
Week 3 | 24 - 28 Aug | Core requirements 4-6 + the technical challenge | All 6 core requirements working, and the project-specific technical challenge implemented and demonstrable. | Checkpoint 3 - code review (feature freeze on Sun 30 Aug)
Week 4 | 29 Aug - 30 Sep | Polish, testing & delivery | Loading / empty / error states, permission flows, validation, 3 unit tests + 1 UI test passing, README with screenshots, signed release build, slides. Stretch requirements only if everything above is done. | Final demo & grading (first week of September)

## Grading Sheet
Evaluation Rubric - 100 Points
Copy this sheet once per team.
Criterion | What it means | Max Points | Score
Core requirements (Req 1-6) | All six core requirements implemented and working. | 25
Technical challenge | The project-specific challenge is solved properly, not faked or worked around. | 15
Code quality & architecture | Clean layering, readable naming, dependency injection, no duplicated logic. | 18
UI / UX & states | Consistent design, all four screen states, sensible permission and error flows. | 12
Stability | No crash in the demo; handles offline, empty data and invalid input. | 8
Testing | 3 unit tests + 1 UI test, meaningful and passing. | 7
Teamwork & Git | Both members contributed throughout and can explain the whole codebase. | 5
Documentation & demo | Complete README with screenshots, and a clear presentation. | 5
Stretch requirements (Req 7-8) | Only counted if all six core requirements are finished first. | 5
TOTAL |  | 100 | 0
Note: | Check the GitHub commit distribution at Checkpoint 1, not at the end - an unbalanced pair is fixable in week 3, not in week 8.